## Slide 1
Lead Orgn - AKRSP (I)
Partner Orgn- DSC
Soochna, Sahbhagita, Sushashan
Grameen Sushashan Pariyojna

## Slide 2: Introduction
Project Title: Strengthening participation in local governance to enhance access to entitlements and basic services by marginalised tribal communities
Duration: 1st March, 2014 to 28th February, 2019
Reporting Period: 1st March, 2014 to 28th Feb 2015
Location: 2 states, 5 districts, 6 blocks, 96 GP
Gujarat - Arvalli, Narmada
MP - Badwani, Khargone, Dhar

## Slide 3: Schemes and Populations
Priority Community Groups: 42000 tribal HH;
population of 2.36 lacs
Total Outreach in year I:
reached to 21023 persons;
Access of benefit:
14096 persons (3096 women)
Priority Schemes:
Sectors | Schemes planned for targeting | Schemes Covered in first year
Health & Nutrition | RSBY, Deen Dayal Health Card, JSY, Chiranjeevi Yojna, ICDS, RBSY | RSBY, Deen Dayal Health Card, JSY
Social Security | Widow, Old Age, Disable Pension, IAY, NREGA, NFSA | Widow, Old Age, Disable Pension, NREGA
Education | Scholarship, Ladli Laxmi Yojana | None
Livelihood | Agriculture Input Supply, Tribal Sub-Plan, BRGF, NRLM | Agriculture Input Supply, Farmers training
Groups/Scheme | Plan to Reach | Reached in year I
Widow | 2273 | 217
Old Age Persons | 5358 | 104
PwD | 1824 | 249
Landless Families | 1186 | 0
PTG | 235 | 0
Farmers/BPL | 20000 | 13413
Total | 30876 | 14096

## Slide 4: Results
Very good collaboration with local government and PRI – PRI members workshop attended by govt officials and elected representatives
Establishment of 8 Nagrik Soochna Kendra out of which 2 are based in panchayat office
Launch of “Kaay Tumaan Khabar Hai” mobiel voice messaging services (VMS) – broadcasting twice in a week – reaching to 1562 persons
Increased participation in gram sabha and polio campaign due to VMS

## Slide 5: Results….
Support to widows in accessing land on their names – 217 women got land on their names
335 Women farmers supported in accessing agriculture schemes
More than 10000 persons got information's about government schemes and services through different mediums
More than 1200 persons received support from NSK in getting basic records or benefit of schemes.

## Slide 6: Results….
Significant change in participation level in gram sabha– over three rounds of gram sabha in last year
Improved participation and registering of demands/issues to gram sabha by women through awareness and mahila sabha
Successful Training, awareness and planning support to GP in meghraj, Sagabara, D.pada - good collaboration with panchayats and government – more than 13000 persons got employment
3 medical certification camps for disable in collaboration with health deptt - mobilisation of more than 800 PwD in sagbara and dpada blocks - AKRSPI team invited at district level for district ability team headed by collector Narmada

## Slide 7: Challenges
To equip our teams for information and procedures – so many schemes, periodic change in eligibility/process
System of tracking at PRI level – for each beneficiary from application to availing benefits
Delayed payments in major social security schemes and NREGA
State govt has not approved new BPL list as per SECCS-2011

## Slide 8: Visibility
Type of activity | Description (purpose of activity) / Date | Target Audience | Impact
Workshop | Project introductory workshop with PRI members | PRI members | Orientation of PRI members about the project, rapport building with PRI members and sarpanch
Workshop | Wokrshop with women's federation with government officials | Women members of federation | Awareness about government schemes - particularly sanitation
Workshop | Awareness camp was held on world disability day | Disable persons and community leaders | Awareness about provisions related to disable persons and how to access the same was created
Voice Messaging Service | Scheme and Services related information broadcasting | Community members | People started accessing schemes and services and improvement in attendance in gram sabha

## Slide 9: Finance and Contract
Total cost of the project: | 11,13,967.00 | EUR | 
EC contribution: | 10,00,000.00 | 89.77% | EU share (%)
Start date | 01/03/2014 | Duration | 
End date | 28/02/2019 | 60 months | 
Costs | All years Contract Budget | Actual expenditures end of Year 1 | Balance
1. Human Resources | 3,84,289 | 6,332 | 3,77,957
2. Travel | 55,165 | 2,844 | 52,321
3. Equipment and supplies | 84,290 | 1,768 | 82,522
4. Local office /Action costs | 83,520 | 2,953 | 80,567
5. Other costs, services | 2,00,753 | 1,572 | 1,99,181
6. Other | 1,83,498 | 1,908 | 1,81,590
7. Subtotal direct costs of the Action (1-6) | 9,91,515 | 17,377 | 9,74,138
8. Contengency reserve | 49,576 | 0 | 49,576
9. Total direct eligible costs | 10,41,091 | 18,246 | 10,22,845
10.Administrative costs (max 7%) | 72,876 | 1,277 | 71,599
Total eligible costs | 11,13,967 | 18,593 | 10,95,374

## Slide 10: Finance..
Low financial expenditure against first year planned budget –
  Preparatory phase took more time in staff recruitment and orientation
  Elections delayed some of the activities
For clarification - Procurement, if done through single party what short of documentation is required.

## Slide 11: Collaborations
What we can offer:
Women and land ownership – specially for widow
Village Planning
What we would like to learn:
Effective use of ICT
Tracking/Monitoring of access to benefits & MIS

## Slide 12
Thanks